Community Service Activity Progress Report

### Project Title

Name: Muhammad Awais

Roll No: 25P-0011 BAI-2A

Name: Waleeja Khan

Roll No: 25P-0005 BAI-2A

Name: Syeda Areej E Fatima

Roll No: 25P-0014 BAI-2A

Name: Syed Shayan Rizvi

Roll No: 25P-0045 BAI-2A

Supervisor Name & Signature

______________________________________

FAST-National University of Computer & Emerging Sciences, Peshawar

- Group Information

| Member Name | Roll Number | Section |
| --- | --- | --- |
| Muhammad Awais | 25P-0011 | BAI-2A |
| Syed Shayan Rizvi | 25P-0045 | BAI-2A |
| Syeda Areej E Fatima | 25P-0014 | BAI-2A |
| Waleeja Khan | 25P-0005 | BAI-2A |

- Activity Overview

  - Project Title: Sahulat Card Documentation Aid.

  - Project Location: Hospital Chowk, Phase 4 Hayatabad, Peshawar.

  - Partner Organization: Hayatabad Medical Complex (HMC)

  - Start Date of Activity: 6th Feb 2026.

  - Expected End Date: 2nd March 2026.

- Objectives of the Project

- Optimize Healthcare Facilities

The first objective is to optimize healthcare facilities by organizing and properly assembling patient files. This project focuses on reducing any errors in file-handling and ensuring that file management processes are quick and efficient for workers. This step reduces the risk of any delay in treatment caused by misplaced data.

- Enhance Safety through Digitalization

To minimize health risks for staff by digitizing patient files and transitioning from physical to digital records. By removing any direct contact with infectious files, the project creates a safer workspace for healthcare workers and prevents the spread of any kind of infection among them. Beyond infection, digitalization protects the records from any physical damage, ensuring long-term data safety.

- Social Responsibility and University’s Objective

To accomplish the university’s mission of community engagement and teamwork by implementing positive societal change. This objective guarantees that the project works as a practical application of university’s values and promotes collaborative efforts to help and improve community.

- Tasks Completed So Far

Proceeding with Sahulat Card Documentation Aid, the team has completed several major tasks at Hayatabad Medical Complex (HMC). There are four major tasks which includes:

- Verification of documents

- Organization of files

- Scanning of records

- Digitalization of files.

Muhammad Awais was responsible for checking conventional documents and assuring that all required documents and official stamps were present in the file.  Syed Shayan Rizvi organized the files by removing the duplicate documents and arranging them in a correct manner. Syeda Areej E Fatima carried out the task of scanning the organized files. Assuring that both sides of pages are scanned and converting them from physical to digital format. Waleeja Khan uploaded the scanned files and made unique folder for each record. Each member has contributed approximately 12 hours of service so far according to the project schedule. The details of the tasks performed, organization name, hours spent, and responsible group members are presented in the table below.

| Task/Activity | Organization | Hours | Date | Group Members |
| --- | --- | --- | --- | --- |
| Verification of documents (Checking paper documents and required stamps) | HMC | 12 | 26-02-26 | Muhammad Awais |
| Data Organization (Separating duplicate documents and organizing it in correct order) | HMC | 12 | 26-02-26 | Syed Shayan Rizvi |
| Scanning organized files (Conversion from conventional to digital documents using scanner) | HMC | 12 | 26-02-26 | Syeda Areej E Fatima |
| Uploading digital files (Creating unique directory for each patient’s record) | HMC | 12 | 26-02-26 | Waleeja Khan |

- Progress Against Timeline

The Initial timeline proposed for Sahulat Card Documentation Aid was from 6th Feb, 2026 to 2nd March, 2026. In this time period, each team member has been working on the tasks assigned to them according to the planned schedule. Till now, 12 of the 15 hours have been completed. Now we are left 3 hours only to complete the remaining tasks of the project.

Overall, the current progress is effectively aligned with the timeline proposed and all the tasks are executed as per the schedule.

- Challenges Faced

- Congested Workspace

The workspace provided was not only congested but made it challenging for the whole group to carry our tasks out as one group. Due to lack of a proper workplace and subsequently our division into subgroups, the pace of carrying our tasks out was significantly reduced.

- Logistical shortcomings

There were limited resources, such as stationery items, scanners, and verification stamps (only one stamp was available in the hospital), which were the main obstacle to verifying and authenticating the record.

This lack of resources created bottlenecks/holdups, forcing the group to rotate responsibilities and prioritize tasks. Consequently, efficiency was reduced, timelines were extended, and the workflow became less streamlined.

- Language Barrier

Whilst we were working at a government hospital, the primary spoken language of the hospital’s staff was Pashto. None of the group members had native or bilingual proficiency in Pashto, which made conversation not only difficult but challenging for the whole group.

- Solutions or Adjustments Made

- Counter to Challenge 1:

During the project, as we were divided into subgroups, we managed to communicate by physical appearance on and off, and sometimes managed through WhatsApp and mobile phone communication.

- Adjustment made for Challenge 2:

To overcome the shortage of stationery items, etc., we divided the work into teams by assigning the tasks individually so that they could work simultaneously on digital tasks. One member was assigned to check/verify the CNIC and other main data of the patient, and the other was deployed for posting the stamp of authentication on each document before uploading the data into the computer system.

- Solution of Challenge 3:

The communication was mostly carried out in English, and services of the fellow group working with us were taken when needed.

- Community Involvement and Impact

The Sahulat Card Documentation Aid was carried out in collaboration with Hayatabad Medical Complex (HMC). This digitalization of files directly involves Hospital staff and IT department. Most importantly, the patients who are getting treatment through Sehat Sahulat Card Aid are the major beneficiaries. Due to the germs on files, the hospital workers, nurses, doctors and attendants were affected with multiple infections but this project helped them reduced the handling of physical files which contributed in better hygiene and lower risk of infections. Accessing of patients’ information have become easy because of Digitalization of records, this helps doctors and other staff members to retrieve the patient records more quickly. The workers in IT department have shown positive feedback regarding efficient work in process of digitalization of files. The team benefitted the staff of IT department by the better organization of records and scanning and uploading it and making it available in soft copy rather than conventional files system. The work completed by the team members supported the IT staff by assisting in their daily workflow and improving record management.

- Upcoming Tasks and Next Steps

| Upcoming Task | Planned Completion Date | Group Members | Notes/Comments |
| --- | --- | --- | --- |
| Applying stamps on documents with missing stamps | 02-03-2026 | Muhammad Awais | Missing credentials such as stamps & signatures are tackled |
| Separating documents with missing stamps | 02-03-2026 | Syed Shayan Rizvi | Segregating files with missing credentials from finalized files |
| Ensuring that the organized documents have all the required credentials e.g. stamps, signatures, CNIC, etc. | 02-03-2026 | Syeda Areej E Fatima | Double checking if the files finalized by the above members have all the required credentials |
| Scanning and uploading the finalized documents | 02-03-2026 | Waleeja Khan | Finalized files are scanned at hardware and uploaded to cloud |

- Additional Support Needed

In the light of all the challenges mentioned above, which we faced so far are dealt with professionally and in compliance with the civil responsibilities. Hence, we hereby state that we do not need any sort of additional support in carrying out our project at Hayatabad Medical Complex.