Project Proposal

### Project Title: Sahulat Card Documentation Aid

Name: Muhammad Awais

Roll No: 25P-0011 BAI-2A

Name: Waleeja Khan

Roll No: 25P-0005 BAI-2A

Name: Syeda Areej E Fatima

Roll No: 25P-0014 BAI-2A

Name: Syed Shayan Rizvi

Roll No: 25P-0045 BAI-2A

Supervisor Name & Signature

______________________________________

FAST-National University of Computer & Emerging Sciences, Peshawar

INTRODUCTION:

Sahulat Card Documentation Aid involves organizing and digitalizing patient files who submit their cases to avail Sehat Sahulat Program services. The project is divided into two steps:

- The first step focuses on carefully organizing the medical records in patient files, by making sure that every important document is present and properly attested.

- The second step focuses on scanning the patient files. It is carried out by setting the correct path directory on PC and uploading digital files of each patient in a unique directory as respective to their unique visit ID.

The target community is that of patients who want the Sehat Sahulat services for their medical treatment. Due to large unorganized dataset and manual file handling; the process is slow. So, we aim to make a change by efficiently assembling the data and by digitalizing it. It will make this process smoother for the patients as well as the healthcare workers.

This issue matters because unorganized files cause inconvenience and delay in patient’s treatment, who need these services. Secondly, the files of patients, which come directly from wards are carriers of germs which put the health of workers at risk because of their direct interaction with the files. Digitalizing them prevents direct interaction with the files as well as improve storage and efficiency.

- Project Goals and Objectives:

The Sahulat Card Documentation Aid aims to improve healthcare services for patients and healthcare workers. By organizing and properly assembling patient files, we aim to reduce any errors in file handling and quick and efficient file management. Also, by digitalizing it we aim to prevent any direct interaction with the infectious files.

By focusing and working on improving the management issues, this project aligns with the university’s mission of community engagement and teamwork. Also, it shows the university’s mission of making a change in society through good and positive steps.

- SDG Alignment

We observed that our work aligns with 5 SDGs out of 17 standards. The detail of each SDG is presented as follows. The Sahulat Card Documentation Aid:

- SDG 3 (Good Health and Well-Being): Our role is to manage patient records, reports, and documentation, and to ensure the accuracy, confidentiality, and secure uploading of the same record to the hospital’s digital portal. Such reliable records are critical for effective diagnosis, treatment, and continuity of healthcare.

- SDG 4 (Quality Education): Our project supported a well-organized record to make the quality education available, providing valuable data for medical researchers and will also help in learning for future healthcare specialists.

- SDG 9 (Industry, Innovation and Infrastructure): By consolidating the digital platforms, our work also aligns with the standards of SDG 9 like building strong infrastructure, promote sustainable industrial development, reduce redundancy, optimize resource use and adopt revolution in healthcare systems that improve efficiency and lower the errors.

- SDG 16 (Peace, Justice and Strong Institutions): The digitization of data enforces transparent record-keeping and the security of patients’ data. Patients will be more comfortable by knowing that their data is secure and in safe hands. Effective system of data management also helps the institution to improve credibility to the community. Log details to access the data also build strong faith of security of patient information and details.

- SDG 17 (Partnerships for the Goals): The capability of sharing the information/data within the hospitals and cross border institutes to dig out the outbreak of a disease in real time like COVID 19, Polio, Dengue, Monkey Pox and so on. It also helps in researchers accelerating discoveries in medicines and health care.

- Project Description:

The Sahulat Card Documentation Aid project is being carried out at Hayatabad Medical Complex in Hayatabad-Phase 4, Peshawar. The project involves digitization of paper documents. The team of 4 students is divided into two groups. Two students organize physical files by arranging documents and verifying attestations. The other two digitize records using multifunction printer that scans both sides of pages and removes blank ones. Each file's unique visit ID is used for naming the unique directories of the patients to prevent data mixing. So far, in 8 hours of project execution, the team organized over 120 files and digitized more than 250 files. Approximately 350 patients from various medical departments will be benefited by the work done so far. The IT Department received direct workflow support, while doctors will gain quicker access to patients’ information.

- Timeline of the project:

The execution of Sahulat Card Documentation Aid started after a proper planning and scheduled timeline to carry out the tasks without any inconvenience. This project will be implemented over four weeks. The team will be dedicating 4 hours a week, 2 hours/day. We initiated this project on 6th Feb, 2026. After the completion of tasks mentioned below, the project will successfully end on 2nd March, 2026.

| Task / Activity | Collaborating Organization | Hours spent | Start Date | End Date | Group members |
| --- | --- | --- | --- | --- | --- |
| Verification of documents (Checking paper documents and required attestation) | HMC | 8 hours | 6th Feb, 2026 | 2nd march, 2026 | Muhammad Awais |
| Data Organization (separating duplicate documents and organizing it in correct order) | HMC | 8 hours | 6th Feb, 2026 | 2nd march, 2026 | Syed Shayan Rizvi |
| Scanning organized files (conversion from conventional to digital documents using scanner) | HMC | 8 hours | 6th Feb, 2026 | 2nd march, 2026 | Syeda Areej E Fatima |
| Uploading digital files (creating unique directory for each patient’s record) | HMC | 8 hours | 6th Feb, 2026 | 2nd march, 2026 | Waleeja Khan |

- Expected Outcomes:

Sahulat Card Documentation Aid will significantly improve hygiene, infection control and will lead to increased efficiency. By the end of this project, we would’ve approximately digitalized 700 patient files. With each patient, there would be at least one attendant, and each file circulates across minimum three or four staff members (nurses, receptionist and doctors), and finally the IT department. So, we are expecting 2,750 people will be benefited in just 8 days.

The short-term outcomes will involve:

- Reduction in physical handling of patient files.

- Eliminate data redundancy

- Ensure data accessibility across medical sectors.

Due to excessive documentation, the IT department has to overwork. Our contribution in digitalized system can lessen their burden.

Dealing with incomplete, misplaced files improves the problem-solving approach of students. The long-term outcomes will involve reduction in documentation stress over hospitals’ budget, as every month of money is spent over the stationary, papers and files and can be utilized in new medical equipment to directly serve the patients. This community service polishes the students by giving practical experience and exposure to a professional environment, and let them learn teamwork by hands on workflow system.